## Sprint0
|  |  | 39 | 39
[5 empty] | 2015-03-08 | 2015-03-09 | 2015-03-10 | 2015-03-11 | 2015-03-12 | 2015-03-13
Story/Task ID | Story/Task | Assignee | Story Points | Task Points | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
QB0S1 | As a guest I should be able to sign up as a user | Mai Belbesy | 5
1 | Create Sequence Diagram |  |  | 0.5
2 | Implementation |  |  | 2
3 | Create User Interface |  |  | 1
4 | Documentation |  |  | 0.5
5 | Research on Tokens |  |  | 0.5
6 | Research Front-end and Back-end Connection |  |  | 0.5
QB0S2 | As a user I should be able to log in | Rana El-Bendary | 5
1 | Create Sequence Diagram |  |  | 0.5
2 | Implementation |  |  | 2
3 | Create User Interface |  |  | 1
4 | Documentation |  |  | 0.5
5 | Research on Tokens |  |  | 0.5
6 | Research Front-end and Back-end Connection |  |  | 0.5
QB0S3 | As a user I should be able to log out | Ahmed Elnashar | 2
1 | Create Sequence Diagram |  |  | 0.25
2 | Implementation |  |  | 0.5
3 | Create User Interface |  |  | 0.25
4 | Documentation |  |  | 0.25
5 | Research on Tokens |  |  | 0.25
6 | Research Front-end and Back-end Connection |  |  | 0.5
QB0S4 | As a user I should be able to view my profile | Mohamed El Behairy | 3
1 | Create Sequence Diagram |  |  | 0.25
2 | Implementation |  |  | 1.25
3 | Create User Interface |  |  | 0.75
4 | Documentation |  |  | 0.25
5 | Research Front-end and Back-end Connection |  |  | 0.5
QB0S5 | As a user I should be able to edit my profile | Mo.Agamia | 5
1 | Create Sequence Diagram |  |  | 1
2 | Implementation |  |  | 2
3 | Create User Interface |  |  | 1
4 | Documentation |  |  | 0.5
5 | Research Front-end and Back-end Connection |  |  | 0.5
QB0S6 | As a user I can create a quest | Ahmed Abdul Badie | 8
1 | Create Sequence Diagram |  |  | 1.5
2 | Implementation |  |  | 3
3 | Create User Interface |  |  | 1.5
4 | Documentation |  |  | 0.5
5 | Research Front-end and Back-end Connection |  |  | 2.5
QB0S7 | As a user I can edit a quest | Ahmed Shaaban | 8
1 | Create Sequence Diagram |  |  | 1.5
2 | Implementation |  |  | 3
3 | Create User Interface |  |  | 1.5
4 | Documentation |  |  | 0.5
5 | Research Front-end and Back-end Connection |  |  | 2.5
QB0S8 | As a user I can delete a quest | Nesreen Mamdouh | 3
1 | Create Sequence Diagram |  |  | 0.25
2 | Implementation |  |  | 1.25
3 | Create User Interface |  |  | 0.75
4 | Documentation |  |  | 0.25
5 | Research Front-end and Back-end Connection |  |  | 0.5